DOCUMENT #4

Feature Breakdown
Document

Every feature divided into atomic build tasks

MyKasih SARA Command Centre

Prepared by Iceberg AI Solutions  |  April 2026  |  CONFIDENTIAL

# Sprint Overview

| Sprint | Goal | Output |
| --- | --- | --- |
| Phase 0 (Today) | Agent fixes + all accounts set up | Voice agent patch live |
| Week 1 | Foundation — DB + Auth + Scaffold | Login + dashboard shell on Vercel |
| Week 2 | Bot pipelines — Voice webhook + WA chatbot | Both channels saving to Supabase |
| Week 3 | Dashboard all 15 pages built | Full CRM live on Vercel, client access |
| Week 4 | UAT + fixes + handover | Signed off, docs delivered |

# Phase 0 — Agent Fixes (Today, ~2hrs)

| # | Task | File | Owner |
| --- | --- | --- | --- |
| 0.1 | Fix non-transferability guardrail in prompt — add explicit "cannot use another person's MyKad" | sara_agent_prompt.md | Avvie |
| 0.2 | Fix language switch logic — maintain EN once switched, never revert | sara_agent_prompt.md | Avvie |
| 0.3 | Upload updated prompt to ElevenLabs agent panel | ElevenLabs dashboard | Avvie |
| 0.4 | Test agent via live link — confirm both fixes | elevenlabs.io/app/talk-to?agent_id=... | Navien |
| 0.5 | Create GitHub repo: mykasih-crm | github.com | Navien |
| 0.6 | Create Supabase project — Singapore region | supabase.com | Navien |
| 0.7 | Run SQL schema migrations (5 tables) | Supabase SQL editor | Navien |
| 0.8 | Create Vercel project — link to GitHub | vercel.com | Navien |

# Week 1 — Foundation (Days 1–4)

## F1.1 — Next.js Project Scaffold

| # | Sub-task | Details |
| --- | --- | --- |
| 1.1.1 | Init Next.js 14 + TypeScript + Tailwind | npx create-next-app@latest mykasih-crm |
| 1.1.2 | Install + init Shadcn UI | npx shadcn-ui@latest init — dark theme |
| 1.1.3 | Install Supabase client | npm install @supabase/supabase-js @supabase/auth-helpers-nextjs |
| 1.1.4 | Install Recharts + Lucide | npm install recharts lucide-react |
| 1.1.5 | Configure global CSS — color tokens, Inter font | app/globals.css |
| 1.1.6 | Set up .env.local with all env vars | .env.local (never commit) |
| 1.1.7 | Create lib/supabase/client.ts + server.ts | Supabase client helpers |
| 1.1.8 | Set up middleware.ts for route protection | Role-based redirects |

## F1.2 — Login Page

| # | Sub-task | Details |
| --- | --- | --- |
| 1.2.1 | Create /login route | app/(auth)/login/page.tsx |
| 1.2.2 | Build login form UI | MyKasih logo, email, password, submit button in #2E7D32 |
| 1.2.3 | Wire Supabase Auth signIn | supabase.auth.signInWithPassword() |
| 1.2.4 | Role lookup after auth | Query users table → get role → store in session |
| 1.2.5 | Role-based redirects | admin/mykasih → /dashboard, qmedia → /analytics, supervisor → /live-monitor |
| 1.2.6 | Error states | Invalid credentials, network error, locked account |

## F1.3 — Dashboard Shell

| # | Sub-task | Details |
| --- | --- | --- |
| 1.3.1 | Build sidebar component | Fixed dark sidebar, sections + nav items, MyKasih logo |
| 1.3.2 | Build topbar component | Search, notifications bell, user avatar + role badge |
| 1.3.3 | Build layout wrapper | app/(dashboard)/layout.tsx |
| 1.3.4 | Build Dashboard Home page | 4 stat cards + bar chart + donut chart + recent table |
| 1.3.5 | Connect stats to Supabase | GET /api/analytics/summary → real data |
| 1.3.6 | Deploy to Vercel | Push to GitHub → auto-deploy, share URL with team |

# Week 2 — Bot Pipelines (Days 5–9)

## F2.1 — ElevenLabs Webhook (Voice)

| # | Sub-task | Details |
| --- | --- | --- |
| 2.1.1 | Create POST /api/webhook/voice | Next.js API route, verify ElevenLabs signature |
| 2.1.2 | Parse ElevenLabs payload | Extract: conversation_id, transcript, duration, metadata |
| 2.1.3 | Insert into calls table | channel=voice, map fields |
| 2.1.4 | Insert transcript rows | Loop through transcript turns → insert each |
| 2.1.5 | Complaint detection | If category=complaint → generate TKT-YYYY-NNNNN → insert ticket |
| 2.1.6 | IC masking | Regex mask: 880512-**-**** before any DB write |
| 2.1.7 | Excel append via n8n | Trigger n8n workflow → append row to master.xlsx in Supabase Storage |
| 2.1.8 | Configure ElevenLabs webhook | Set webhook URL in ElevenLabs agent settings → test end-to-end |

## F2.2 — Kasih WhatsApp Chatbot

| # | Sub-task | Details |
| --- | --- | --- |
| 2.2.1 | n8n workflow: receive Meta WA webhook | Verify Meta token, extract message body + wa_number |
| 2.2.2 | Intent classification | POST to Claude API with message → return intent label |
| 2.2.3 | FAQ handler | Match intent → query kb_entries → return BM or EN answer |
| 2.2.4 | Balance check handler | Collect IC via follow-up message → mock API → return balance, expiry, nearest merchant |
| 2.2.5 | Merchant lookup handler | Extract state/city → query kb_merchant_directory.txt → top 3 results |
| 2.2.6 | Complaint handler | Collect category + description → create ticket → send reference number |
| 2.2.7 | Quick reply buttons | First message → send 4 buttons via Meta API |
| 2.2.8 | Save to Supabase | channel=chat, insert calls + transcripts rows |
| 2.2.9 | n8n: send WA reply | POST to Meta Cloud API with response text |
| 2.2.10 | Test end-to-end in Testing Console | Use chatbot simulator tab |

# Week 3 — Dashboard Pages (Days 10–16)

| Page | Key Components | Day |
| --- | --- | --- |
| Voice Calls | Filterable table, transcript modal, Excel export, channel badge | 10 |
| Chat Messages | Chat thread view, intent badge, linked ticket | 10 |
| All Interactions | Combined table, channel toggle filter | 11 |
| Tickets | Kanban (open/in-progress/resolved), reference no, masked IC, transcript link | 11 |
| Beneficiaries | WA number lookup, interaction history, ticket history | 12 |
| Live Monitor | Active ElevenLabs sessions via API, active WA chats, status dots | 12 |
| Analytics | Weekly/monthly bar charts, CSAT line, language donut, peak heatmap | 13 |
| Knowledge Base | CRUD table, BM/EN toggle, active switch, sync button | 13 |
| Staff Management | User table, add/edit/remove, role select, last login | 14 |
| Integrations | 4 integration cards with live status, webhook test buttons | 14 |
| Testing Console | 3-tab: ElevenLabs embed + chatbot sim + Anam AI embed | 15 |
| AI Demo Page | Standalone Anam AI persona embed, clean client-facing layout | 15 |
| Settings | Agent hours config, webhook URLs, notification prefs | 16 |

# Week 4 — UAT + Handover (Days 17–21)

| # | Task | Owner |
| --- | --- | --- |
| 4.1 | 40 test calls — 10 per category (eligibility, FAQ, merchant, complaint), split BM/EN | Avvie + Navien |
| 4.2 | Document pass/fail for each test call in Testing Console | Navien |
| 4.3 | Latency benchmark — all responses < 2 seconds | Avvie |
| 4.4 | PDPA audit — verify IC masking end-to-end, check Supabase records | Navien |
| 4.5 | MyKasih KB review — team approves all knowledge base content | MyKasih team |
| 4.6 | Bug fix sprint — resolve all UAT failures, re-test | Avvie + Navien |
| 4.7 | Export UAT report from Testing Console | Navien |
| 4.8 | Architecture diagram + n8n export + ElevenLabs config docs | Naveen |
| 4.9 | Training session — walk MyKasih + QMedia through dashboard | Navien |
| 4.10 | Handover package — all credentials, configs, docs | Navien |